## create an excel sheet with the
Sprint | Task ID | User Story ID | Task Description | Assignee | Priority | Estimated MD | Remaining MD | Status | Notes
Sprint 1 | 1 | US1 | Identifying load cell for monitoring the weight of the gas cylinder.The load cell should be able to identify gas change as small as 100g. |  | High | 3 | 3 | Done
Sprint 1 | 2 | US2 | Selection and evaluation of LPG gas sensor based on sensitivity and response time |  | High | 3 | 3 | Done |  | Low | To Do
Sprint 1 | 3 | US3 | Conduct a feasibility check for including an automatic shut-off valve in case of occurance high risk gas leak |  | High | 3 | 3 | In Progress |  | Medium | In Progress
Sprint 1 | 4 | US4 | Identifying the suitable evaluation platform for data processing operation. |  | High | 2 | 2 | Done |  | High | Done
Sprint 1 | 5 | US5 | Evaluate the power requirement for entire system and select suitable voltage source.Estimate voltage and current requirement for stable operation. |  | High | 3 | 3 | In Progress
Sprint 2 | 6 | US6 | Create first level documents and add the documents into git repository |  | High | 2 | 2 | Done
Sprint 2 | 7 | US7 | Review the datasheet of selected components and learn its behaviour to ensure that the components meet the final product requirement |  | High | 3 | 3 | Done
Sprint 3 | 8 | US8 | Procurement of load cell with HX711 module,MQ2,MQ4,MQ7 gas sensors, DHT22 |  | High |  |  | Done |  | Name2
Sprint 3 | 9 | US9 | Write the driver code and header files for reading data from MQ2,MQ4 and MQ7 gas sensor |  | High | 3 | 3 | Done
Sprint 3 | 10 | US10 | Read ADC values by interfacing MQ2,MQ4 and MQ7 gas sensor |  | High | 3 | 3 | Done
| 11 | US11 | Write the .c and .h files for reading data from loadcell with HX711 module |  | High | 3 | 3 | In Progress
Sprint 3 | 12 | US12 | Read load cell values with HX711 module using a known weight |  | High | 3 | 3 | In Progress
| 13 | US13 | Write the .c and .h files for reading data from DHT22 temp and humidity sensor |  | High | 3 | 3 | In Progress
| 14 | US14 | Test the gas sensors using smoke or butane source to ensure that PPM concentration changes unlike the readings in clean air. |  | High | 3 | 3 | To Do
Sprint 4 | 15 | US15 | Interfacing gas sensor with processing platform to test leak detection |  | Low | 3 | 3 | To Do
Sprint 4 | 16 | US16 | Interfacing load cell with processing platform for weight monitoring |  | Low | 7 |  | To Do
Sprint 5 | 17 | US17 | Developing algorithm for user behaviour analysis,prediction ,leak detection and anomaly detection . |  | Low | 5 |  | To Do
Sprint 6 | 18 | US18 | Integration of modules and testing the behaviour |  | Low | 7 |  | To Do
Abbreviations
| PS | Platform Setup
| DRV | Driver and RTOS integration
| APP | Application
| QA | Quality Assurance